## Sheet1
Requirements | Description | Status | Verification Method | Verification Status | Comments
0. Key Milestones | Delivery of full end to end system and documentation | In Work | Delivery | In Work
1. Acquire hardware | Acquisition of all major hardware components | Complete | Delivery | Complete
2. Install and run software | Installation and execution of all major software components on RasPi | In Work | System Test | In Work
3. Integration | Test of individual processes and links between software components | In Work | System Demonstration | Not Started
3.6 End to End system function | Full execution of system chain - Receiving UHF signal in ATSC, convert ATSC data stream to transport stream, convert transport stream to mp4 format, display of mp4 format, observation from network connected device | Not Started | System Demonstration | Not Started | All components of system talking to each other
4. Documentation | Delivery of all documentation required | In Work | Delivery | Not Started
1. Acquire hardware | Acquisition of all major hardware components | Complete | Delivery | Complete | 0
1.1 Single-board Computer | Acquire Raspberry Pi 5 (RP5) | Complete | Delivery | Complete
1.2 Software Defined Radio | Acquire Software Defined Radio (SDR) capable of receiving UHF satcom signals | Complete | Delivery | Complete | RSPdx-R2
1.3 UHF Antenna | Acquire antenna that can receive UHF satcom signal | Complete | Delivery | Complete | SMA-W100RX2
2. Install and run software | Installation and execution of all major software components on RasPi | In Work | System Test | In Work | 0
2.1 PiOS | Base operating system for RP5 functionality | Complete | System test | Complete | Using PiSDR custom software image
2.2 GNU Radio | Installation of GNURadio Software onto RP5 | Complete | System test | Complete | Using PiSDR custom software image
2.3 SDRPlay | Installation of SDRPlay SDR software onto RP5 | Complete | System test | Complete | Using PiSDR custom software image; primarily for troubleshooting signals
2.4 TVHeadend | Installation of TVHeadend on RP5 | Complete | System test | Not Started
3. Integration | Test of individual processes and links between software components | In Work | System Demonstration | Not Started | 0
3.1 Receive UHF signal | Receive UHF satcom signal and view within SDRPlay software | Complete | System demonstration | Complete | Signal received via computer using same software setup as RasPi
3.2 Receive ATSC Transport stream | Create GNU Radio receiver translation flow that converts received signal into transport stream | In Work | System demonstration | Not Started | Block diagrams in work
3.3 Convert transport stream into video format | Convert transport stream into video format | In Work | System demonstration | Not Started | Within GNU radio
3.4 View mp4 from external device | View mp4 from external device (such as a laptop or desktop) connected via Local Area Network (LAN) | In Work | System demonstration | Not Started | Requires TVHeadend
3.5 View data stream translation to mp4 from UHF signal | Confirm GNU radio system functionality | In Work | System demonstration | Not Started | Requires full GNU Radio scripts
3.6 End to End system function | Full execution of system chain - Receiving UHF signal in ATSC, convert ATSC data stream to transport stream, convert transport stream to mp4 format, display of mp4 format, observation from network connected device | Not Started | System Demonstration | Not Started | All components of system talking to each other
3.7 Docker Container | Containerization of deployed RasPi Software components | In Work | System test | Not Started
4. Documentation | Delivery of all documentation required | In Work | Delivery | Not Started | 0
4.1 Requirements Matrix | Creation of requirements matrix for tracking of milestones | Complete | N/A
4.2 Wire flow diagram | Creation of wire diagram to show data flow of system | Complete | N/A
4.3 Demo video | Demonstration of end-to-end system compatibility | Not started | System Demonstration | Not Started | Requires fully functional end to end system
4.4 Process documentation | Delivery of all text components and documentation | In Work | N/A